## Design & Constr (sample)
SAMPLE FOR ILLUSTRATION -- PLEASE USE TAB LABELED "Design & Construction (blank)"
Standard Budget Form (Construction)
Grantee Name:
Facility Name:
Project Title:
|  | Expense Category |  |  |  | Total | Cost Sharing
| Task | Direct Labor and Related-Party Labor (not more than 25%) | Contractor Expense (including any Contractor-Paid Equipment or Materials) | Equipment and Materials (if not included under Contractor Expense) | Other Direct Costs (e.g. fees, freight)* | Total | MassCEC Grant for Phase ($) (not more than 50% of total) | Grantee Share ($)
Design Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Initial design | 2000 | 15000 |  |  | 17000
| Subcontractor A |  |  |  |  | 0
| Subcontractor B |  |  |  |  | 0
| Submit license amendment |  |  |  |  | 0
| Submit interconnection application |  | 5000 |  |  | 5000
| Design modifications, if necessary | 1000 | 4000 |  |  | 5000
| Application for LIHI certification |  |  |  | 2000 | 2000
| Application for MA RPS qualification |  |  |  |  | 0
Design Phase totals |  | 3000 | 24000 | 0 | 2000 | 29000 | 14000 | 15000
% of Phase Total |  | 10.34% |  |  |  |  | 48.28% | 51.72%
Construction Phase (customize task list as appropriate; add rows to a task if multiple contractors participating)
| Equipment order |  |  | 100000 | 10000 | 110000
Subcontractor C
Subcontractor D
| Equipment removal |  |  |  |  | 0
| Equipment refurbishment |  | 10000 |  |  | 10000
| Site work, construction | 10000 |  | 10000 |  | 20000
| Joe's Excavating |  | 100000 |  |  | 100000
| ACME Concrete |  | 50000 |  |  | 50000
| Equipment installation |  |  | 40000 |  | 40000
| Complete interconnection |  |  | 30000 |  | 30000
| Construction Oversight/PM |  |  | 20000 |  | 20000
| Commissioning |  |  |  |  | 0
| Register and report to PTS |  |  |  |  | 0
| Contingency |  |  |  |  | 40000
Construction Phase totals |  | 10000 | 160000 | 200000 | 10000 | 420000 | 200000 | 220000
% of Phase Total |  | 2.381% |  |  |  |  | 47.62% | 52.38%
Budget Summary
Total Project Costs, All Phases | [5 empty] | 449000 | Percentage of Total
Total MassCEC Grant Request | [5 empty] | 214000 | 47.66%
Total Grantee Cost Share | [5 empty] | 235000 | 52.34%

## Design & Constr (blank)
Instructions for completing this form are found in the Reference Materials
Commonwealth Hydropower
Standard Budget Form (Construction)
Grantee Name:
Facility Name:
Project Title:
|  | Expense Category |  |  |  | Total | Cost Sharing
| Task | Direct Labor or Related-Party Labor (not more than 25%) | Contractor Expense (including any Contractor-Paid Equipment or Materials) | Equipment or Materials (if not included under Contractor Expense) | Other Direct Costs (e.g. fees, freight) | Total | MassCEC Grant for Phase ($) (not more than 50% of total) | Grantee Share ($)
Design Phase
| Initial design |  |  |  |  | 0
| Subcontractor A |  |  |  |  | 0
| Subcontractor B |  |  |  |  | 0
| Submit license amendment |  |  |  |  | 0
| Submit interconnection application |  |  |  |  | 0
| Design modifications, if necessary |  |  |  |  | 0
| Application for LIHI certification |  |  |  |  | 0
| Application for MA RPS qualification |  |  |  |  | 0
Design Phase totals |  | 0 | 0 | 0 | 0 | 0 |  | 0
% of Phase Total |  | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
Construction Phase
| Equipment order |  |  |  |  | 0
Subcontractor C
Subcontractor D
| Equipment removal |  |  |  |  | 0
| Equipment refurbishment |  |  |  |  | 0
| Site work, construction |  |  |  |  | 0
| Contractor 1 |  |  |  |  | 0
| Contractor 2 |  |  |  |  | 0
| Equipment installation |  |  |  |  | 0
| Complete interconnection |  |  |  |  | 0
| Construction Oversight/PM |  |  |  |  | 0
| Commissioning |  |  |  |  | 0
| Register and report to PTS |  |  |  |  | 0
| Contingency |  |  |  |  | 0
Construction Phase totals |  | 0 | 0 | 0 | 0 | 0 |  | 0
% of Phase Total |  | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
Budget Summary
Total Project Costs, All Phases | [5 empty] | 0 | Percentage of Total
Total Grant | [5 empty] | 0 | #DIV/0!
Total Grantee Share ($) | [5 empty] | 0 | #DIV/0!

## Supporting Sched
Supporting Schedule
Task | Detail (e.g., Company/Vendor, Item, Labor Category) | Unit Cost | Number of Units | Other | Total | Comment